## Agenda
KAIZEN EVENT — FIVE-DAY AGENDA
Event name:
Process / value stream:
Dates:
Location:
Sponsor:
Team leader:
Facilitator:
Target metric and baseline:
Day | Block | Activity | Output you must have before moving on | Owner
Pre-week | T-2 weeks | Scope the event: one process, one metric, boundaries agreed in writing | Charter signed by the sponsor
Pre-week | T-1 week | Confirm team, book the room for all five days, pull baseline data | Baseline nobody disputes later
Day 1 | AM | Train the team on the tools they will actually use this week | Everyone can read the current-state map
Day 1 | PM | Walk the process. Map current state on the floor, not in the room | Current-state map with real cycle times
Day 2 | AM | Measure: cycle times, waiting, rework, distance, inventory | Data on the map, not adjectives
Day 2 | PM | Analyse causes of the biggest gaps (5 Whys / fishbone / Pareto) | Verified causes, not first guesses
Day 3 | AM | Design future state. Generate options before choosing one | Future-state map plus the trade-offs rejected
Day 3 | PM | Try the change physically — move the bench, change the sequence | Something different is running by end of day
Day 4 | AM | Measure the trial against the baseline. Adjust or revert | Numbers from the trial, honest ones
Day 4 | PM | Standardise: work instructions, visual controls, training | Standard work the operators helped write
Day 5 | AM | Build the 30-day action list for what did not fit in the week | Owner and date on every open item
Day 5 | PM | Report out to the sponsor. Agree the follow-up review date | Sponsor commitment on record
Follow-up | Day 30 | Verify the gain held. Close or reopen | Metric re-measured against baseline
Free kaizen event agenda and role card — 5xwhys.com/articles/rca/kaizen-event/ · A kaizen event without a Day 30 verification is a workshop, not an improvement

## Roles
KAIZEN EVENT — WHO IS IN THE ROOM AND WHAT THEY OWN
Role | Owns | In the room? | Failure mode when the role is missing
Sponsor | Scope, resources, removing blockers, accepting the result | Day 1 open and Day 5 report-out | Team improves something nobody asked for and the change is reversed in a month
Team leader | The process being improved; lives with the result afterwards | All week | Standard work is written by visitors and quietly abandoned
Facilitator | Method, pace, keeping the team on evidence | All week | Week turns into a discussion of opinions and ends in a list of wishes
Operators | How the work is really done today | All week | The map describes the procedure, not reality — the classic reason gains do not appear
Support functions | Maintenance, quality, IT, scheduling — whatever the change touches | On call, booked in advance | Day 3 trial stalls waiting for someone who was never told
Finance / controlling | Agreeing how the saving is counted, before the week starts | Day 1 and Day 5 | Sponsor and team disagree afterwards about whether anything was gained